## Start here
{ medtrics }
ACGME Annual-Cycle Tracker
Every task from "Streamlining ACGME Accreditation: Run the Year, Not the Visit" as a working plan.
How to use this workbook
1. Put real names in the Owner column at your next program or GME-office meeting: an unowned row is a risk, not a plan.
2. Enter YOUR program's ADS Important Dates as the outer wall, then set the internal deadline at least a week earlier.
3. Update Status as you go. The dropdown keeps it consistent (Not started / In progress / Done / Blocked).
4. Revisit the Standing rows every year; they are what makes next season a plan instead of a scramble.
Verified against ACGME primary sources on September 1, 2026: Common Program Requirements (four versions effective July 1, 2026) and ACGME e-communications of June 22 and July 6, 2026 covering the AY 2026-2027 ADS Annual Update. The authoritative version of every requirement is the current edition on acgme.org.
From the Medtrics Outcomes library: medtricslab.com/evidence

## Tracker
Phase | Task | Suggested owner | Timing | Status | Notes
Standing (every year) | Pull current ACGME requirement documents (Common Program Requirements; your specialty's Program Requirements; Institutional Requirements) and record each effective date | Accreditation lead / program coordinator | At academic-year rollover (July) |  | Never work from a saved copy; diff against last year's editions
Standing (every year) | Check the current acgme.org pages for site visits; self-study; and any initiative your plans cite; note what changed | Named owner (program or GME office) | At academic-year rollover |  | The current page wins any argument with a summary; including this tracker's notes
Standing (every year) | Update the owner column of this tracker for departures and role changes | Program director + coordinator | At academic-year rollover |  | Turnover should cost a person; never a process
Standing (every year) | Maintain rosters; evaluations; and program records continuously | Program coordinator + data owners | All year |  | Short update seasons are earned all year
Season start | Review resident and fellow records after the academic-year rollover (records move to Unconfirmed status) | Program coordinator | Late June to July |  | Per ACGME e-communication June 22 2026 (AY 2026-2027 rollover)
Season start | Read your program's Important Dates view in ADS and calendar your Annual Update timeframe | Program coordinator | By early July |  | Timeframes posted by July 1 for AY 2026-2027
Season start | Read the ACGME's initial notification email and list this year's requirements and deadlines in this tracker | Program coordinator | Start of reporting window |  | Per ACGME e-communication July 6 2026
Season start | Book the program director's working time for the update season | Program coordinator | Start of window |  | An hour held in July beats the same hour in the closing week
Season start | Set the internal deadline at least one week before the date shown in ADS | Program director | Start of window |  | Reserve room for the DIO round trip
Annual Update window (July-September 2026) | Confirm every resident and fellow record: arrivals; departures; transfers; status changes | Program coordinator | Early in your window |  | Nothing looks broken until each record is checked
Annual Update window (July-September 2026) | Assign each update section a data owner and a due date inside the internal deadline | Program director | Early in your window |  | The update is a program task; not a one-person form
Annual Update window (July-September 2026) | Complete the pieces that need the program director personally | Program director | Mid-window |  | Uses the time booked at season start
Annual Update window (July-September 2026) | Run an internal consistency review before anything goes to the DIO | Program director + coordinator | Before internal deadline |  | One source system per answer; flag gaps honestly
Annual Update window (July-September 2026) | Send the completed update to the DIO with room for a possible return | Program director | Internal deadline |  | DIO review step per ACGME help-center overview (process effective July 1 2021); confirm mechanics with your GME office
Annual Update window (July-September 2026) | Track DIO approval; or handle a return and resubmit before the window closes | Program coordinator | Before ADS close date |  | A return the day before close is the scramble this tracker prevents
Milestones and other reporting | Enter your specialty's Milestones reporting windows in this tracker | Program coordinator | At season start |  | See the companion Milestones reporting guide for current requirements
Milestones and other reporting | Calendar any other ACGME-set dates from official correspondence | Program coordinator | As received |  | ACGME-set dates override everything in this tracker
After the season | Archive submission confirmations and correspondence in the shared repository | Program coordinator | Within one month of window close |  | Next season inherits an archive; not a mystery
After the season | Debrief: list what was reconstructed late this year that should be maintained all year | Program director + DIO office | Within one month of window close |  | Feed the answers back into the Standing phase