## Start here
{ medtrics }
AVMA COE Accreditation Tracker
Every task from 'Managing AVMA COE Accreditation: The Self-Study, the Annual Report, and the Visit' as a working plan.
How to use this workbook
1. Put real names in the Owner column at your next leadership meeting. An unowned row is a risk, not a plan.
2. Set target dates from YOUR visit date, working backward (the Timing column is a reminder, not a COE deadline).
3. Update Status as you go. The dropdown keeps it consistent (Not started / In progress / Done / Blocked).
4. Revisit the Standing rows every year. They are what makes the next cycle a plan instead of a folder.
Verified against AVMA Council on Education primary sources (Policies and Procedures, July 2025 edition; Appendix E; classifications; accredited-colleges list; FAQs) on September 1, 2026. The authoritative version of every requirement is the current edition on avma.org. The FAQ's six-week / 100-page self-study figures conflict with the P&P (twelve weeks, 105 pages); this tracker plans against the P&P. Confirm the date that binds your visit in writing.
From the Medtrics Evidence Library. Independent operational guide; not AVMA or COE guidance. Nothing here promises an accreditation outcome.

## Checklist
Phase | Task | Suggested owner | Timing | Status | Notes
Standing (every year) | Pull the current Accreditation Policies and Procedures of the AVMA Council on Education from avma.org and record the edition date | Accreditation lead | Annual |  | Never work from a saved copy; the edition fetched for this guide is dated July 2025
Standing (every year) | Pull current Appendix E Self-Study Guidelines and Appendix K Annual Interim Report Guidelines and diff against last year's files | Accreditation lead | Annual |  | Evidence required for each Standard lives in Appendix E
Standing (every year) | Update the standard-owner list for departures and role changes | Accreditation lead | Annual |  | Owner = person who can produce the evidence and the narrative
Standing (every year) | File the annual interim report (Accredited colleges) unless a visit just happened or is due in the first six months of the following year | Accreditation lead | Per COE schedule |  | The Council requires an annual interim report from each college with Accredited status
Standing (every year) | Screen planned changes (enrollment; sites; distance education; mission) for substantive-change approval BEFORE implementation | Dean + accreditation lead | Before decisions are final |  | The COE must grant approval prior to implementation of any substantive change
Standing (every year) | Inspect off-campus required training sites in person | Clinical education office | No less than annually |  | Standard 3: directly (in-person) and regularly (no less than annually)
Standing (every year) | Refresh outcomes tables (NAVLE school score reports; attrition; employment; graduate and employer feedback) | Outcomes data steward | Annual |  | Each institution reports 5 years of NAVLE results in the annual interim report and in self-studies
Owners | Assign a named owner to every one of the eleven Standards of Accreditation | Dean + accreditation lead | This term |  | Eleven standards numbered 1 through 11
Owners | Name a standing data steward for outcomes tables | Outcomes data steward | This term |  | Narratives that contradict tables are a records problem
Visit prep | Confirm the next comprehensive visit date from COE correspondence and the public accredited-colleges list; enter it in this tracker | Accreditation lead | When known |  | Site visits at intervals of not more than seven years; plan against YOUR date
Visit prep | At the nine-month alert: pull the current P&P; charge the self-study committees; lock the owner list | Dean + accreditation lead | At least nine months before the end of the period |  | P&P 2.3.1: the dean is alerted to the requirements for preliminary reports
Visit prep | Draft the self-study against Appendix E from standing records; not from a visit-year excavation | Standard owners | Working backward from the filing date |  | The self-study report is the single most important document of the accreditation process
Visit prep | File the self-study with AVMA and with each site team member | Accreditation lead | No later than twelve weeks before the site visit |  | P&P 2.2.2. The COE FAQ says six weeks; plan against twelve unless your COE contact confirms otherwise in writing
Visit prep | Keep the self-study at or under the page cap with readable type | Accreditation lead | Before filing |  | The self-study should not be more than 105 pages in total; inclusive of appendices; minimum size 11 font
Visit prep | Consistency pass: narratives versus NAVLE; attrition; employment; and the nine-competency record | Outcomes data steward | Before filing |  | One source system per table
Visit prep | Confirm Standard 9 instructional weeks from the live curriculum record | Curriculum dean | Before filing |  | at least 130 weeks of direct instruction; a minimum of 40 weeks of hands-on clinical education
Visit prep | Brief interview participants on the sections covering their own area | Standard owners | Final weeks before the visit |  | The visit verifies the self-study; it does not invent the record
After the visit | If the Council assigns deficiencies: treat each as a project with an owner and a due date | Accreditation lead | Immediately after the letter |  | Minor deficiencies: one year. Probationary: two years. Confirm current rules in the P&P.
After the visit | Archive the full cycle (self-study; report of evaluation; correspondence; this tracker) in the shared location | Accreditation lead | Within one month of the decision |  | The folder named COE 2018 should be a running archive; not a mystery