## Start here
CCNE accreditation tracker
Start here
This workbook is a planning tracker for baccalaureate, master's, DNP, and post-graduate APRN certificate programs. It is not CCNE guidance and it does not promise an accreditation outcome.
How to use it
1. Open the Tracker tab. Put real names in the Suggested owner column at your next leadership meeting.
2. Confirm the next on-site year from CCNE correspondence and the public directory. Enter it in the notes for the Confirm the next on-site year row.
3. If that year is 2027 or later, lock the Amended 2026 Standards as the working set. If a self-study will be uploaded in 2026 for a 2027 visit, confirm in writing that the 2026 Standards govern.
4. Use the Status dropdown (Not started / In progress / Done / N/A). Do not invent extra statuses.
5. A plain CSV of the same rows is available for Google Sheets or another importer.
Verification
Verified against CCNE primary sources on September 1, 2026: Standards for Accreditation (Amended 2024 and Amended 2026), Procedures (amended January 14, 2025), the July 7, 2026 Board announcement, General Advice (July 2026), and the CIPR and new-applicant pages. The current files on ccneaccreditation.org remain the only authoritative statement of any requirement.
Edition clock (do not skip)
2024 Standards remain in effect through December 31, 2026. 2026 Standards go into effect January 1, 2027. A 2027 on-site is written to the 2026 Standards even if the self-study is uploaded in 2026, unless CCNE staff confirms otherwise in writing.
Evidence Library
Companion article: Managing CCNE Accreditation: Two Editions, the Self-Study, and the CIPR (slug streamlining-ccne-accreditation). Independent operational guide from Medtrics. CCNE and AACN are named descriptively.

## Tracker
Phase | Task | Suggested owner | Timing | Status | Notes
Standing (every year) | Pull the current Standards edition that will govern the next on-site from the CCNE site and record the edition date | Accreditation lead | Annual |  | Never work from a saved copy. Amended 2024 remains in effect through December 31 2026. Amended 2026 takes effect January 1 2027.
Standing (every year) | Pull current Procedures (amended January 14 2025 unless a later file is posted) and General Advice and diff against last year's files | Accreditation lead | Annual |  | Procedures for Accreditation of Baccalaureate and Graduate Nursing Programs
Standing (every year) | Update the standard-owner list for departures and role changes | Accreditation lead | Annual |  | Owner = person who can produce the evidence and the narrative
Standing (every year) | File the annual report | Chief nurse administrator | Per CCNE schedule |  | The chief nurse administrator of a program that holds CCNE accreditation is required each year to submit a report to CCNE
Standing (every year) | Screen planned changes (new tracks; sites; program additions or closures) for substantive-change notification | Dean + chief nurse administrator | Before decisions are final |  | The substantive change notification must be received by CCNE no earlier than 90 days prior to implementation or occurrence of the change; and no later than 90 days after
Owners | Assign a named owner to every one of the four Standards in the edition that will govern the next on-site | Dean + accreditation lead | This term |  | Standard I Mission and Governance; Standard II Institutional Commitment and Resources; Standard III Curriculum and Teaching-Learning Practices; Standard IV Assessment and Achievement of Program Outcomes
Owners | Name a standing data steward for outcomes tables (completion; licensure; certification; employment; graduate and employer feedback) | Outcomes data steward | This term |  | Narratives that contradict tables are a records problem. This page reports no program's rates.
Owners | Name a CIPR owner now; do not invent one in year five | Accreditation lead | This term |  | A Continuous Improvement Progress Report is generally submitted at the mid-point of the accreditation term
Edition clock | If the next on-site is in 2027 or later: lock the 2026 Standards as the working set; pull the 2018-2026 crosswalk | Accreditation lead | When the date is known |  | July 7 2026 Board announcement: hosting an on-site evaluation and/or submitting a report on or after January 1 2027 requires the 2026 Standards
Edition clock | If a self-study will be uploaded in 2026 for a 2027 on-site: confirm in writing that the 2026 Standards govern; put the confirmation in this tracker | Accreditation lead | When the visit year is known |  | The Board announcement includes a self-study submitted prior to January 1 2027 for an on-site occurring in 2027. The Standards HTML page says reports submitted before that date address 2024. Plan against the visit year.
Edition clock | If a CIPR is due in December 2026: use the December 2026 submissions template; do not mix it with the March 2026 general template | CIPR owner | Before drafting |  | CIPR Template for December 2026 Submissions Only
Visit prep | Confirm the next on-site year from CCNE correspondence and the public directory of accredited programs; enter it in this tracker | Accreditation lead | When known |  | Continued accreditation may be granted for a maximum period of 10 years; plan against YOUR date
Visit prep | Schedule the on-site with CCNE | Accreditation lead | A minimum of 12 months in advance |  | Spring evaluations are generally January through April; fall evaluations are generally September through November
Visit prep | Charge standard owners; pull the matching self-study template (2024 or 2026) | Dean + accreditation lead | When scheduled |  | Use the template that matches the edition that governs the visit
Visit prep | Draft one self-study for all programs under review; organized by standard and key element | Standard owners | Working backward from the filing date |  | A single self-study document addressing all programs under review must be developed
Visit prep | Develop the agenda and share it with the team leader | Chief nurse administrator | No later than 8 weeks prior |  | General Advice: develop the agenda no later than 8 weeks prior to the evaluation
Visit prep | Notify constituents of the opportunity to submit third-party comments | Chief nurse administrator | At least 2 months before the on-site |  | CCNE receives written third-party comments until 21 days before the scheduled on-site evaluation
Visit prep | File the self-study (including appendices); Program Information Form; agenda; and third-party-comment verification | Accreditation lead | No later than 6 weeks prior |  | The program must submit the self-study document ensuring that they are received by CCNE no later than 6 weeks prior to the scheduled on-site evaluation
Visit prep | Keep the self-study at or under the narrative page cap | Accreditation lead | Before filing |  | no longer than 110 pages of narrative for one or two degree or certificate programs; and no longer than 120 pages of narrative for three or four
Visit prep | Stand up the virtual resource room organized by standard and key element | Accreditation lead | At least 7 days prior |  | the program must provide the team access to evaluation resource materials at least 7 days prior to the CCNE on-site evaluation
Visit prep | Consistency pass: narratives versus completion; licensure; certification; and employment tables | Outcomes data steward | Before filing |  | One source system per table. This page reports no program's rates.
Visit prep | Brief interview participants on the sections covering their own area | Standard owners | Final weeks before the visit |  | The visit verifies the self-study; it does not invent the record
CIPR | Draft the CIPR against the current template; do not alter standard; key element; or elaboration statements | CIPR owner | Mid-point of the term |  | The completed CIPR should not exceed 95 pages. The page limit does not include appendices.
CIPR | Submit the CIPR on or before the due date and no sooner than 30 days before | CIPR owner | Per CCNE letter |  | All reports must be submitted on or before the due date (but no sooner than 30 days before the due date)
After the visit | If the Board requests additional reporting: treat each item as a project with an owner and a due date | Accreditation lead | Immediately after the letter |  | Follow-up is a project; not a letter to file
After the visit | Archive the full cycle (self-study; team report; program response; correspondence; this tracker) in the shared location | Accreditation lead | Within one month of the decision |  | The folder named CCNE 2018 should be a running archive; not a mystery

## Edition clock
Which Standards edition governs the next on-site?
When | What it means for the tracker
July 7, 2026 | CCNE Board approved the Amended 2026 Standards after a focused review of the 2024 Standards.
Through December 31, 2026 | 2024 Standards remain in effect. On-sites before January 1, 2027 are assessed using 2024.
January 1, 2027 | 2026 Standards go into effect. On-sites and reports on or after this date address 2026.
Self-study filed in 2026 for a 2027 visit | The July 7, 2026 announcement includes a self-study submitted prior to January 1, 2027 for an on-site occurring in 2027. Confirm in writing. Plan against the visit year.
Your date | The next-evaluation year in CCNE correspondence and the public directory is the date to plan against, not a typical interval. Continued accreditation may be granted for a maximum period of 10 years.
Authoritative files live on ccneaccreditation.org. This sheet is a reminder, not a substitute.