## Edition transition
Phase | Task | Suggested owner | Timing | Status | Notes
Standing (every year) | Pull the current COM Continuing Accreditation Standards from osteopathic.org and record the edition date | Accreditation lead | At the start of each academic year |  | Never work from a saved copy; the 2026 edition is effective July 1 2026
Standing (every year) | Confirm whether Standard 12 applies (only if COCA is the institutional accreditor) | Accreditation lead | At the start of each academic year |  | Standards 1-11 are required for full programmatic accreditation
Standing (every year) | If the COM is applicant or pre-accredited pull the New and Developing Standards instead of (or in addition to) the continuing set | Accreditation lead | At the start of each academic year |  | Do not mix the two binders
Standing (every year) | Download the current reporting tables that accompany the edition in force | Accreditation lead | With the standards pull |  | Tables change with the edition
Standing (every year) | Update the owner column of this tracker for departures and role changes | Dean + accreditation lead | At the start of each academic year |  | Turnover should cost a person; never a process
Edition transition (2026) | Read COCA's published comparison of the 2023 and 2026 continuing standards | Accreditation lead | Before the next review |  | The comparison is the first diff; not a later one
Edition transition (2026) | Diff every tracked element against the 2026 table of contents; retire 2023-only rows | Accreditation lead | Before any review after Feb 1 2027 |  | Reviews after February 1 2027 run against the 2026 edition
Edition transition (2026) | Note elements the 2026 edition names that your 2023 tracker did not (for example 6.12 nutrition; 11.4 COMLEX-USA as its own element) | Curriculum dean + outcomes owner | During the diff |  | Confirm current numbering on osteopathic.org; do not trust a prior crosswalk
Owners | Assign a named owner to every element in the edition that will govern the next review | Dean + accreditation lead | This term |  | The owner produces the evidence; not the most senior person nearby
Owners | Name a standing data steward for outcome tables (COMLEX-USA; GME placement; graduation and retention) | Outcomes owner | This term |  | Narratives that contradict tables are a records problem
Evidence (all year) | Keep curriculum maps; OPP/OMM instruction; and clinical-site comparability current as standing records | Curriculum dean | All year |  | Hours reconstructed in a visit year are not hours
Evidence (all year) | Keep affiliation agreements with expiration status in one access-controlled place | Clinical education office | All year |  | Agreement review should be a filter; not a file hunt
Evidence (all year) | Keep COMLEX-USA cohort files under school control (import; not a live feed) | Outcomes owner | As results arrive |  | The school files its own reports
Self-study and review | Read the current self-study process in the standards document that governs your review | Accreditation lead | When a review is scheduled |  | Do not restate the process from memory
Self-study and review | Calendar the review date; if it falls after February 1 2027 lock the 2026 edition as the working set | Accreditation lead | When the date is known |  | The review date chooses the edition
Self-study and review | Run a mock visit against the edition in force; not the prior one | Accreditation lead | Final months before the visit |  | A mock built on 2023 is a rehearsal of the wrong play
After the review | Archive correspondence and progress-report requirements with owners and due dates | Accreditation lead | Within one month of the decision |  | Follow-up is a project; not a letter to file