## Start here
{ medtrics }
LCME Readiness Checklist
Every task from 'Managing LCME Accreditation: An Operational Guide to the Self-Study, DCI, and ISA' — as a working plan.
How to use this workbook
1. Put real names in the Owner column at your next leadership meeting — an unowned row is a risk, not a plan.
2. Set target dates from YOUR visit date, working backward (the Timing column gives the typical lead time).
3. Update Status as you go — the dropdown keeps it consistent (Not started / In progress / Done / Blocked).
4. Revisit the Standing rows every year; they are what makes the next cycle a plan instead of a folder.
Verified against LCME primary sources (2026-27 Functions and Structure, current DCI and ISA materials) on August 16, 2026. The authoritative version of every requirement is the current edition on lcme.org.
From the Medtrics Evidence Library — medtricslab.com/evidence

## Checklist
Phase | Task | Suggested owner | Timing (relative to site visit) | Status | Notes
Standing (every year) | Pull current-year LCME documents from lcme.org (Functions and Structure; DCI; ISA materials; self-study and survey guides) and diff against last year's editions | Accreditation lead | Annual |  | Never work from a saved copy; note renumbered or reworded elements
Standing (every year) | Update the element-owner list for departures and role changes | Accreditation lead | Annual |  | Owner = person who can produce the data and narrative
Standing (every year) | Annual refresh pass on the master DCI (data tables + narratives) | DCI data steward | Annual |  | Continuous DCI beats visit-year archaeology
Standing (every year) | Submit LCME annual questionnaires and any required status reports on time | Accreditation lead | Per LCME schedule |  | LCME-set dates override everything in this tracker
Standing (every year) | Screen planned changes (class size / curriculum / campuses) for LCME notification requirements | Dean + accreditation lead | Before decisions are final |  | Check current LCME rules on substantial change
Kickoff | Confirm visit cycle and key LCME dates from official correspondence; enter them in this tracker | Accreditation lead | T-24 to T-18 months |  | Schedule everything backward from LCME-set dates
Kickoff | Appoint accreditation lead with authority and protected time | Dean | T-24 to T-18 months |  | If this is someone's fifth job the timeline is fiction
Kickoff | Charge the self-study task force; dean kicks off personally | Dean | T-24 to T-18 months |  | Visible sponsorship unblocks element owners later
Kickoff | Assign a named owner to every element in the current standards edition | Accreditation lead | T-24 to T-18 months |  | Put it in writing; keep it living
Kickoff | Stand up the master DCI for the visit-year edition in a shared access-controlled location | DCI data steward | T-24 to T-18 months |  | One live master copy; no private forks
Kickoff | Form the ISA student committee and confirm its independence and support logistics | Student affairs (logistics only) | T-24 to T-18 months |  | Students run analyze and write it; the school does not steer findings
Production | Element owners draft DCI narratives and data tables against real source systems | Element owners | T-18 to T-6 months |  | One source system per table; flag gaps honestly
Production | ISA committee fields its student survey and builds response rates | ISA student committee | T-18 to T-12 months |  | Response-rate building takes a full term
Production | ISA committee analyzes results and writes the ISA report | ISA student committee | T-12 to T-6 months |  | Must finish before self-study synthesis starts
Production | Standard-by-standard subcommittee review; problems flagged and remediation started | Task force subcommittees | T-18 to T-6 months |  | Problems found now are fixable; found by the team they are findings
Production | Consistency pass: narratives vs data tables vs ISA | DCI data steward | T-9 to T-6 months |  | Contradictions between sections are the classic site-visit stumble
Synthesis | Write the self-study summary from DCI + ISA with candid weaknesses and concrete plans | Accreditation lead + task force | T-6 to T-3 months |  | A no-problems self-study is implausible not reassuring
Synthesis | Dean and leadership review and sign off on the full package | Dean | T-4 to T-3 months |  | Leadership reads the whole thing before the survey team does
Synthesis | Submit required documents to the LCME by its stated deadlines | Accreditation lead | Per LCME schedule |  | Save submission confirmations to the archive
Rehearsal | Run a mock visit with external reviewers who have survey experience | Accreditation lead | T-4 to T-2 months |  | Fix what it finds; rehearse answers with evidence not polish
Rehearsal | Brief every interview participant on the sections covering their own area | Element owners | T-2 months to visit |  | People should recognize their own data when asked
Rehearsal | Finalize visit logistics: schedule; rooms; documents; escorts; tech | Accreditation lead | T-2 months to visit |  | Confirm details against the survey team's requests
After the visit | Log every flagged element as a project with an owner and due date | Accreditation lead | Immediately after findings |  | Follow-up is a project not a letter to file
After the visit | Write status reports from the remediation project records | Element owners | Per LCME schedule |  | Evidence of change beats narrative of intent
After the visit | Archive the full cycle (DCI; ISA; self-study; correspondence; this tracker) in the shared location | Accreditation lead | T+1 month |  | The next team should inherit an archive not a mystery