## Start here
Mock site-visit checklist (2026)
Start here
1. Pick the body first.
Name LCME, ACGME (program vs Sponsoring Institution), COCA, or AVMA COE on Checklist row 1. Dates that body publishes override the suggested timing.
2. Put real names in the Suggested owner column.
Do that at the next leadership meeting. If the mock owner is somebody's fifth job, the timeline is fiction.
3. Freeze the packet, then rehearse.
A mock visit rehearses the documents surveyors will hold. Edits after freeze go on a parking list.
4. Status dropdown.
Not started / In progress / Done / Parked. Parked means the finding waits for the next cycle or a clarifying-materials request.
Verification note
Verified against primary site-visit and survey pages fetched September 1, 2026 (ACGME Site Visit FAQ and June 2026 ADS checklist; COCA Policies and Procedures Rev 2026; AVMA COE FAQs and Appendix I July 2025; LCME publications, Secretariat ISA webinar, and an LCME-hosted Academic Medicine article describing the typical full-survey interval). A mock visit is this guide's operating model, not a requirement those bodies publish. Confirm the date that binds your visit in writing. Current pages on the accreditor's site remain the only authoritative statement of any rule.
Evidence Library
Companion article: Mock Site Visits: Who Owns the Rehearsal, What to Freeze, and When. Slug mock-site-visits-prepare-for-success. Independent operational guide from Medtrics. Not LCME, ACGME, COCA, or AVMA guidance. Nothing here promises an accreditation outcome.
CCNE, ACEN, and other bodies not fetched for the article are out of scope. Do not stretch this protocol onto a survey page you have not opened.

## Checklist
Phase | Task | Suggested owner | Timing | Status | Notes
Pick the body | Name the accreditor and the visit type (program vs Sponsoring Institution; comprehensive vs focused; full survey vs random sample) on row one of this tracker | Accreditation lead | Before any rehearsal is scheduled | Not started | If you cannot name the body and the visit type you do not yet have a mock to schedule
Pick the body | ACGME programs: do not schedule a year-out mock as if a 10-Year Accreditation Site Visit were still assigned | Program director + coordinator | When a visit is possible | Not started | The ACGME discontinued the program 10-Year Accreditation Site Visit effective October 2023
Pick the body | ACGME programs: treat random sampling and annual-data-triggered visits as live possibilities | DIO + program coordinator | Standing | Not started | programs are eligible if they have not had a site visit in nine years or more
Pick the body | ACGME Sponsoring Institutions: keep the 10-Year Accreditation Site Visit on the institutional calendar | DIO + institutional coordinator | Standing | Not started | All Sponsoring Institutions undergo a 10-Year Accreditation Site Visit
Pick the body | LCME: pull current survey-year DCI ISA self-study and survey-visit guides from lcme.org; enter the correspondence date | Accreditation lead | When the survey year is known | Not started | established MD programs as typically undergoing a full survey every eight years; plan against YOUR date
Pick the body | COCA: calendar the staff contact that sets comprehensive visit dates | Accreditation lead | When COCA writes | Not started | COCA staff will contact a college of osteopathic medicine approximately 12 months before the anticipated comprehensive site visit
Pick the body | AVMA COE: enter the next visit date from COE correspondence and confirm the self-study filing date in writing | Accreditation lead | When known | Not started | A given school has a COE site visit at not more than a seven-year interval
Owners | Name a mock owner with authority over freeze date interview roster agenda and debrief | Dean or DIO | Before freeze | Not started | If this role is somebody's fifth job the checklist below is fiction
Owners | Name a document-freeze owner who can stop edits | Accreditation lead | Before freeze | Not started | After freeze new evidence goes on a parking list
Owners | Name an interview-roster owner who builds the list to the body's published rules | Accreditation lead | Before freeze | Not started | Do not hand-pick only the most polished speakers
Document freeze (ACGME) | Update ADS by the due date in the Site Visit Announcement letter and lock uploads | Program or institutional coordinator | Due date in the announcement letter | Not started | Failure to update the ADS information may result in a postponement of the site visit and assessment of a $3
Document freeze (ACGME) | Inventory documents from the announcement letter not from last year's binder | Coordinator | When the letter posts | Not started | Document lists appear as in the Site Visit Announcement letter
Document freeze (ACGME) | Upload the signed Site Visit Attestation Statement | DIO or program director | Before the visit | Not started | All Sponsoring Institutions and programs must upload a signed Site Visit Attestation Statement prior to the visit
Document freeze (ACGME) | Do not rehearse Self-Study interviews Field Representatives have been told not to run | Mock owner | When building the agenda | Not started | Effective July 1 2025 the Self-Study requirements are no longer being monitored
Document freeze (LCME) | Freeze the DCI/self-study as submitted plus the ISA incorporated into that submission | Accreditation lead | After submission; before the survey visit | Not started | A mock that interviews against a later draft of the DCI is a rehearsal of a document the survey team does not have
Document freeze (COCA) | Freeze the self-study filed in the electronic accreditation system | Accreditation lead | No later than 90 days before the site visit begins | Not started | Self-studies must be submitted no later than 90 days before the site visit begins
Document freeze (COCA) | Park anything not requested as clarifying materials | Accreditation lead | Two weeks before through visit day | Not started | No materials will be accepted during a site visit without approval from the site visit Team Chair
Document freeze (AVMA COE) | Freeze the self-study sent to the site team; score the mock against Appendix I as a snapshot of current conditions | Accreditation lead | No later than six weeks before the visit (FAQ; confirm in writing) | Not started | the self-study is presented to the site visit team no later than six weeks before the visit
Interview roster | ACGME program visits: PD coordinator DIO/chair faculty and residents and fellows per Field Activities FAQ | Mock owner | Before mock day | Not started | For small programs Field Representatives interview all residents and fellows on duty that day
Interview roster | Exclude learners beyond required years from the ACGME resident and fellow interview | Roster owner | When building the list | Not started | Learners beyond the required years of residency may not participate in the resident and fellow interview
Interview roster | Use peer-selected residents and fellows from all required years in larger ACGME programs | Roster owner | When building the list | Not started | for larger programs peer-selected representatives from all required years
Interview roster | COCA AVMA COE and LCME: include students; do not substitute a dean-picked panel for the body's student session | Roster owner | When building the list | Not started | Do not hand-pick only the most polished speakers
Rehearsal | Run the day on the real agenda shape (opening document review interviews closing clarification) | Mock owner | After freeze; far enough before the real visit to fix packet contradictions | Not started | this guide's own operating model; it is not a published accreditor requirement
Rehearsal | Debrief every finding as packet contradiction missing document interview-rule break or logistics miss; assign owner and due date | Mock owner | Same day as the mock | Not started | The mock does not predict the accreditation decision
Rehearsal | ACGME: remember Field Representatives will not offer predictions regarding accreditation or recognition outcomes; neither should the mock team | Mock owner | Debrief | Not started | Accreditation Field Representatives will not offer predictions regarding accreditation or recognition outcomes
After | Archive freeze packet roster agenda debrief and this tracker in the shared location | Accreditation lead | Within one month | Not started | Turnover should cost you a person never the freeze date
Evidence Library footer. Article: Mock Site Visits: Who Owns the Rehearsal, What to Freeze, and When. Independent operational guide from Medtrics. Not accreditor guidance. Nothing here promises an accreditation outcome. Verified September 1, 2026.